## Summary
BFCM 2026 · Deliverables progress
Counts update from the Done column on the Paid and Organic tabs.
Group | Sheet | Total | Done | % done
Hype | Paid
Launch | Paid
Mid-sale gifting | Paid
Ending soon | Paid
Paid dependencies | Paid
Social post | Organic
Owned / site | Organic
All deliverables
Legend
Yellow cells (Done column): pick Yes when the deliverable is finished. The row greys out.
Status dropdown: Not started, In progress, In review, Done, Blocked.
Example: a finished hype ad reads Done = Yes, Status = Done, Notes = "Live in Meta, ad set Hype 1".
Assumptions
Dimensions are standard Meta and organic sizes, not a DiggerLid spec: video (9:16, 4:5); image (4:5, 1:1, 9:16); GIF (4:5, 1:1); UGC and episodes (9:16); email (600 px wide); pages (desktop + mobile).
Ad lines, posts and dates come from the BFCM 2026 Sale Plan deck as of 19 Oct 2026. Owners are placeholders.
Proposed, not agreed: edit due dates (2 days before each post) and the partner UGC dates.

## Paid
BFCM 2026 · Paid deliverables checklist (47 ads + dependencies)
Tick Done with the dropdown (Yes). Status, Owner and Notes are yours to edit. Dimensions sit in brackets on each line.
Done | Phase | Live from | Deliverable (dimensions) | Format | Footage / source | Owner | Due | Status | Notes
| Hype | 2026-11-17 | Air Walk / Crush: Jack hook, then sale graphics #1 (9:16, 4:5) | Video | Location TBC | Creative [name] |  | Not started
| Hype | 2026-11-17 | Air Walk / Crush: Jack hook, then sale graphics #2 (9:16, 4:5) | Video | Location TBC | Creative [name] |  | Not started
| Hype | 2026-11-17 | Bundle image, paddock (4:5, 1:1, 9:16) | Image | Paddock | Creative [name] |  | Not started
| Hype | 2026-11-17 | Bundle image, warehouse (4:5, 1:1, 9:16) | Image | Warehouse (shot) | Creative [name] |  | Not started
| Hype | 2026-11-17 | AI static with the sale info #1 (4:5, 1:1, 9:16) | Image | Generated | Creative [name] |  | Not started
| Hype | 2026-11-17 | AI static with the sale info #2 (4:5, 1:1, 9:16) | Image | Generated | Creative [name] |  | Not started
| Hype | 2026-11-17 | All Up Here / Bucket Head, 15 to 20 sec (9:16, 4:5) | Video | Warehouse (shot) | Creative [name] |  | Not started
| Hype | 2026-11-17 | Show You A Thing Or Two, 15 to 20 sec (9:16, 4:5) | Video | Paddock | Creative [name] |  | Not started
| Hype | 2026-11-17 | Fake Phone Call, hype version (9:16, 4:5) | Video | Paddock, from the ute | Creative [name] |  | Not started
| Launch | 2026-11-19 | Infomercial #1: whip cuts, quick script (9:16, 4:5) | Video | Warehouse (shot) | Creative [name] |  | Not started
| Launch | 2026-11-19 | Infomercial #2: hook, demo table + B-roll (9:16, 4:5) | Video | Warehouse (shot) | Creative [name] |  | Not started
| Launch | 2026-11-19 | Usage video: bundle + free gift, PRO Mat, Pro Enclosure (9:16, 4:5) | Video | Paddock | Creative [name] |  | Not started
| Launch | 2026-11-19 | Bundle image #1 (4:5, 1:1, 9:16) | Image | Warehouse (shot) | Creative [name] |  | Not started
| Launch | 2026-11-19 | Bundle image #2 (4:5, 1:1, 9:16) | Image | Warehouse (shot) | Creative [name] |  | Not started
| Launch | 2026-11-19 | AI image with the sale info #1 (4:5, 1:1, 9:16) | Image | Generated | Creative [name] |  | Not started
| Launch | 2026-11-19 | AI image with the sale info #2 (4:5, 1:1, 9:16) | Image | Generated | Creative [name] |  | Not started
| Launch | 2026-11-19 | BFCM GIF: offer + countdown #1 (4:5, 1:1) | GIF | Graphics | Creative [name] |  | Not started
| Launch | 2026-11-19 | BFCM GIF: offer + countdown #2 (4:5, 1:1) | GIF | Graphics | Creative [name] |  | Not started
| Launch | 2026-11-19 | UGC creative #1 (9:16) | UGC | Creators | Creative [name] |  | Not started
| Launch | 2026-11-19 | UGC creative #2 (9:16) | UGC | Creators | Creative [name] |  | Not started
| Launch | 2026-11-19 | UGC creative #3 (9:16) | UGC | Creators | Creative [name] |  | Not started
| Launch | 2026-11-19 | UGC creative #4 (9:16) | UGC | Creators | Creative [name] |  | Not started
| Launch | 2026-11-19 | All Up Here infomercial: Jack out cold across the products (9:16, 4:5) | Video | Warehouse (shot) | Creative [name] |  | Not started
| Launch | 2026-11-19 | Look Earthmovers, 45 sec (9:16, 4:5) | Video | Paddock | Creative [name] |  | Not started
| Launch | 2026-11-19 | All products + bundles with Jack out cold (4:5, 1:1, 9:16) | Image | Warehouse (shot) | Creative [name] |  | Not started
| Launch | 2026-11-19 | Theme GIF: Jack moments on loop #1 (4:5, 1:1) | GIF | All shoot days | Creative [name] |  | Not started
| Launch | 2026-11-19 | Theme GIF: Jack moments on loop #2 (4:5, 1:1) | GIF | All shoot days | Creative [name] |  | Not started
| Launch | 2026-11-19 | Fake Phone Call, launch version with B-roll + offer overlays (9:16, 4:5) | Video | Paddock | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Titan Sox creator: collab pack unboxed as a gift #1 (9:16) | UGC | Titan Sox creators | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Titan Sox creator: collab pack unboxed as a gift #2 (9:16) | UGC | Titan Sox creators | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | 3DPro creator: the buckets, then the full pack #1 (9:16) | UGC | 3DPro creators | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | 3DPro creator: the buckets, then the full pack #2 (9:16) | UGC | 3DPro creators | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Gift buyer POV: PRO Mat Plus unboxed (9:16) | UGC | Customer / creator | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Tradie opening the gift on site (9:16) | UGC | Customer / creator | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Stocking filler under $50: caddy or phone cradle (9:16) | UGC | Customer | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Too Good To Keep: Ep 3 cut-down (9:16, 4:5) | Video | Worksite | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Collab pack reveal at [$X] (9:16, 4:5) | Video | Worksite stills | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Gift guide video: PRO Mat Plus in four colours + order-by dates (9:16, 4:5) | Video | All shoot days | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Collab pack hero static: 3 brands, 1 pack (4:5, 1:1, 9:16) | Image | Worksite stills | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Gifts by price: $39, $49, $299, bundles from $732 (4:5, 1:1, 9:16) | Image | Product shots | Creative [name] |  | Not started
| Mid-sale gifting | 2026-11-23 | Order-by dates by state (+ Black Friday version) (4:5, 1:1, 9:16) | Image | Graphics | Creative [name] |  | Not started
| Ending soon | 2026-11-29 | Departure finale cut-down (concept TBC) #1 (9:16, 4:5) | Video | Departure | Creative [name] |  | Not started
| Ending soon | 2026-11-29 | Departure finale cut-down (concept TBC) #2 (9:16, 4:5) | Video | Departure | Creative [name] |  | Not started
| Ending soon | 2026-11-29 | Countdown static: 3 days left / last day #1 (4:5, 1:1, 9:16) | Image | Graphics | Creative [name] |  | Not started
| Ending soon | 2026-11-29 | Countdown static: 3 days left / last day #2 (4:5, 1:1, 9:16) | Image | Graphics | Creative [name] |  | Not started
| Ending soon | 2026-11-29 | Countdown GIF (4:5, 1:1) | GIF | Graphics | Creative [name] |  | Not started
| Ending soon | 2026-11-29 | Ending-soon UGC (concept TBC) (9:16) | UGC | TBC | Creative [name] |  | Not started
| Paid dependencies |  | Partner UGC briefs agreed with Titan Sox and 3DPro | Admin | Partners | Growth [name] | 2026-11-02 | Not started
| Paid dependencies |  | Usage rights for paid ads on all UGC | Admin | Partners | Growth [name] | 2026-11-09 | Not started
| Paid dependencies |  | Partner UGC delivered | Admin | Partners | Growth [name] | 2026-11-16 | Not started
| Paid dependencies |  | Gifting page offer set for the mid-sale ads | Admin | Site | Growth [name] | 2026-11-20 | Not started
| Paid dependencies |  | All ad sets built and scheduled | Admin | Meta | Paid [name] | 2026-11-16 | Not started

## Organic
BFCM 2026 · Organic and owned deliverables checklist
Tick Done with the dropdown (Yes). Status, Owner and Notes are yours to edit. Dimensions sit in brackets on each line.
Done | Phase | Live from | Deliverable (dimensions) | Format | Footage / source | Owner | Due | Status | Notes
| Social post | 2026-11-12 | Teaser: Jack's coming to town (9:16) | Short | Warehouse (shot) | Creative [name] | 2026-11-10 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-15 | Teaser: the call, AI took the jobs gag (9:16) | Short | Paddock | Creative [name] | 2026-11-13 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-17 | Ep 1 · Warehouse: meeting the boys, 90 sec (9:16) | Episode | Warehouse (shot) | Creative [name] | 2026-11-15 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-18 | Bonus · SANY yard + China: the deal (9:16) | Episode | SANY yard + China cutaway | Creative [name] | 2026-11-16 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-19 | Ep 2 · Paddock: the proper way, 90 sec, 12 PM (9:16) | Episode | Paddock | Creative [name] | 2026-11-17 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-21 | Short: Jack's tips (outtakes) (9:16) | Short | Paddock + warehouse | Creative [name] | 2026-11-19 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-23 | Ep 3 · Worksite: the lessons stick, 90 sec (9:16) | Episode | Worksite | Creative [name] | 2026-11-21 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-25 | Collab pack reveal, joint post with Titan Sox + 3DPro (4:5, 9:16) | Static + story | Worksite stills | Creative [name] | 2026-11-23 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-27 | Short: Black Friday, 7 AM (9:16) | Short | Any episode | Creative [name] | 2026-11-25 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-29 | Finale · Departure: heading home, 90 sec (9:16) | Episode | Departure | Creative [name] | 2026-11-27 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-11-30 | Short: Cyber Monday, 7 AM (9:16) | Short | Finale cut-down | Creative [name] | 2026-11-28 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-12-01 | Last day: Good trip. Got the boys sorted. (9:16) | Short | Finale | Creative [name] | 2026-11-29 | Not started | Edit due 2 days before post (proposal)
| Social post | 2026-12-03 | Bloopers and thanks + shipping cut-offs (9:16) | Short | All shoot days | Creative [name] | 2026-12-01 | Not started | Edit due 2 days before post (proposal)
| Owned / site |  | Email template: launch (600 px wide) | Email |  | Email [name] |  | Not started | Due TBC
| Owned / site |  | Email template: mid-sale gifting (600 px wide) | Email |  | Email [name] |  | Not started | Due TBC
| Owned / site |  | Email template: Black Friday (600 px wide) | Email |  | Email [name] |  | Not started | Due TBC
| Owned / site |  | Email template: close / last day (600 px wide) | Email |  | Email [name] |  | Not started | Due TBC
| Owned / site |  | SMS: launch | SMS |  | Email [name] |  | Not started | Due TBC
| Owned / site |  | SMS: last day | SMS |  | Email [name] |  | Not started | Due TBC
| Owned / site |  | Sale landing page (desktop + mobile) | Page |  | Web [name] | 2026-11-13 | Not started
| Owned / site |  | Bundle page (desktop + mobile) | Page |  | Web [name] | 2026-11-13 | Not started
| Owned / site |  | Collection page (desktop + mobile) | Page |  | Web [name] | 2026-11-13 | Not started
| Owned / site |  | Early-access capture page (desktop + mobile) | Page |  | Web [name] | 2026-11-13 | Not started
| Owned / site |  | Gifting landing page, own offer + discounts (desktop + mobile) | Page |  | Web [name] | 2026-11-20 | Not started
| Owned / site |  | Gift guide (desktop + mobile) | Page |  | Web [name] | 2026-11-20 | Not started
| Owned / site |  | Christmas cut-off banner (desktop + mobile) | Banner |  | Web [name] | 2026-11-20 | Not started
| Owned / site |  | Collab pack set up in store at [$X] | Store setup |  | Growth [name] | 2026-11-20 | Not started
| Owned / site |  | Popup reach above 50% on paid pages | Check |  | Web [name] | 2026-10-15 | Not started
| Owned / site |  | Bundle and gift-tier stills, 12 (4:5, 1:1) | Stills |  | Creative [name] |  | Not started | Due Shot