# Father's Day 2026 Campaign Brief

Campaign Period: 26 Aug – 4 Sep 2026 (10-day sale) · Pre-sale launch sent 9 Aug · Post-Father's-Day flash 7–8 Sep

Duration: 10-day sale + 48-hour post-event flash

Campaign Type: Seasonal Sale (gifting)

Hero Concept: The Father's Day gift he'll actually use — the work mat that goes from under the machine midweek to the family on weekends.

Hero Line: "The Father's Day gift he'll actually use"

Australian Father's Day: Sunday 6 September 2026. The sale ends two days before (Fri 4 Sep) to protect shipping; a post-event self-buy flash follows the day after.

## GACC Strategic Core

### G — Goal

Drive gift-buyers and self-buyers to Pro Mat Plus and multi-mat bundles, lifting basket size while protecting margin through a discount month.

| Metric | Target |
| --- | --- |
| AOV | ≥ $315 |
| Effective discount | ≤ 20% (headline 15% on mats) |
| Sale CPA | ≤ $55 (or list-driven, ~$0) |
| MER (sale month) | ≤ 33% |
| GPAM | ≥ break-even (~19.5%), protect toward 22%+ |
| Bundle attach rate | ≥ 30% of orders |
| Gift vs self split | Captured via ALIA poll |
| Contribution | Toward the locked September +$50k net target |

Revenue and GPAM dollars finalise in the margin model once component prices and Pro Mat COGS are confirmed.

### A — Audience

- Primary: Gift-buyers — partners, kids and family of tradies, operators and hands-on dads, motivated by finding "something he'll actually use" rather than another novelty gift.

- Secondary: Self-buyers and existing customers — operators, mechanics, 4WD and hunting dads treating themselves; the repeat list carries discounted volume at zero CPA.

- Avoid: Generic clearance or percent-off framing; cold paid spend behind deep discount; any spend behind loss-making lines (grease couplers contribute negative before ad spend).

### C — Creative

Tone: Practical · straight-talking · warm · dry larrikin humour. Not corporate, not gimmicky, not salesy.

Visual world:

- Pro Mat Plus in real use — under the mini-ex or ute midweek, out with the family on the weekend.

- The four colour personas: Safety Orange (site-to-weekend all-rounder), High Country Camo (hunter / 4WD), Safety Pink (the dad who doesn't do boring), plus the fourth colourway.

- Real tradie dads, kids, dogs, paddocks and jobsites. Verified-review proof on screen.

Hard no's:

- Never use the "We're Diggin' It" tagline — anywhere, any channel.

- No deep-discount, clearance or "everything must go" look.

- Don't hero the Original over the Plus.

- No generic corporate stock-photo gifting.

Creative Pillars

| Pillar | Description | Example Line |
| --- | --- | --- |
| Actually useful | The anti-novelty gift — he uses it every job | "The gift he'll actually use." |
| Site-to-weekend | One mat, work and play | "Under the machine all week. Out with the family on Sunday." |
| Proven by dads | Review-led social proof | "Every year customers tell us the same thing: he actually uses it." |
| Generous gift | Bundles and multi-mat make it feel like a present | "Two mats, free shipping, and something extra for Dad." |

### C — Channels

| Channel | Role | Notes |
| --- | --- | --- |
| Email | Primary demand driver | 5 sends + the already-sent launch; zero-CPA list carries the discount |
| SMS | Single hard-deadline nudge | 2 Sep, on the remote-state shipping cutoff |
| Meta | Prospecting + retargeting | Gift-buyer audiences; efficient core only; sale CPA ≤ $55 |
| Website / CRO | Convert and route | Gift collection, Build-Your-Pack, state-aware shipping countdown, ALIA gift/self poll |
| Organic social | Colour-persona content + UGC | Extends the launch creative and review wall |

## Headline System

Hero (desire): The Father's Day gift he'll actually use.

Subhead (function): 15% off mats · 2 for $499 + free shipping · order by 2–3 Sep for delivery · sale ends 4 Sep.

Rule: Headline = emotion (the useful gift). Subhead = mechanics (offer, cutoff, end date). Always both.

## Core Mechanic (non-negotiable)

- 15% off mats — Pro Mat Plus is the hero and the headline. A shallower cut than 20% protects GPAM while still giving a real reason to buy.

- 2 for $499 + free shipping — the flagship multi-buy (2 × Pro Mat Plus, mix any colours; ~$99 saving). Already live from the 9 Aug launch; it stays the anchor offer through the campaign.

- Tradie Dad Packs — bundles bake in the mat discount and ladder AOV rather than discounting deeper.

- GWP (healthily priced) — free branded Cap or Keyring, shown at its RRP, on orders over ~$300. Low COGS and a high-value threshold keep it margin-safe while making the gift feel generous.

- Post-Father's-Day flash — "Didn't get what you wanted": a 20% self-buy offer, 48 hours, list-only (zero CPA), launching the day after Father's Day.

Rule: This is a gifting and product campaign at ≤20% effective discount. Value lives in the bundle, not the depth. Pro-Mat-led only — the highest-AOV product is the only one that clears CPA at a discount. The list carries the discounted volume; never put cold paid spend behind a deep discount, and never stack the 15% on the 2-for-$499 pack.

### Offer structure (Option A — confirmed direction)

The standing 2-for-$499 remains the flagship multi-buy for the whole period. The 26 Aug sale layers 15% off single mats and the accessory bundles around it. No stacking on the 2-pack. This keeps one consistent multi-buy in market; the sale widens the range and adds urgency plus the post-event flash.

### Bundles — Tradie Dad Packs

Indicative pricing on confirmed mat prices (Pro Mat Plus $299, Original $219, 2-for-$499). Accessory prices to confirm before final pricing.

| Bundle | Indicative price | Contents | Role |
| --- | --- | --- | --- |
| The Site Sorter | ~$309 | Pro Mat Plus + Magnetic Tool Mat + Boom Bottle Opener | Entry gift |
| The Two-Machine Pack | ~$549 | 2 × Pro Mat Plus (the 2-for-$499 core) + Digger Wipes + GWP | Hero — push this |
| The Full Rig | ~$599 | Pro Mat Plus + a Cover + Magnetic Tool Mat + Digger Wipes | Premium |
| The Depot | ~$879 | 2 × Pro Mat Plus + Cover + Magnetic Tool Mat + Digger Wipes + Bottle Opener + GWP | Big-ticket / whole-yard |

Every pack heroes Pro Mat Plus and never sells it alone, fixing the sold-alone AOV dilution. The ladder ($309 to $879) sits well above a solo mat, so the sale lifts basket size instead of eroding it.

## Channel-Specific Plans

### Email Plan

| Email | Date | Time (AEST) | Purpose |
| --- | --- | --- | --- |
| Launch (sent) | 9 Aug | 05:30 | Pro Mat Plus launch, 2-for-$499, review proof |
| E1 — Sale Launch | 26 Aug | AM | Open the sale: 15% off mats, meet the packs |
| E2 — Proof + Hero | 30 Aug | AM | Reviews / UGC + push the Two-Machine Pack |
| E3 — Cutoffs + Ending | 1 Sep | AM | Both state shipping cutoffs + gift-card fallback + sale ending |
| E4 — Sale Ends Tonight | 4 Sep | AM/PM | Final call; gift card for post-cutoff states |
| E5 — Post-FD Flash | 7 Sep | AM | "Didn't get what you wanted" — 20% self-buy, 48h |

Mandatory in every email: Pro Mat Plus hero image, the offer, the relevant shipping cutoff or end date, review proof, clear single CTA, DiggerLid branding without the tagline.

### SMS

One send: Tue 2 Sep, on the remote-state cutoff.

Copy: "DiggerLid: Last day to order for Father's Day delivery — QLD, SA, NT, WA, TAS. 15% off mats + free shipping on 2-packs. Shop → [link]"

### Meta Micro-Brief

- Role: Acquire gift-buyers and retarget warm audiences into the sale and bundles. The post-FD flash is list and retargeting only — no cold spend.

- Phasing: Days 1–4 (26–29 Aug) prospecting on the gift angle and colour personas; Days 5–8 (30 Aug–2 Sep) retargeting, bundles and shipping urgency; 3–4 Sep last-chance and gift card.

- End-frames: Pro Mat Plus, the offer, the shipping cutoff, single CTA. No tagline.

- Guardrails: Pause LPV Flagship and TOF-Broad before launch — do not stack a discount on broken-MER prospecting. Exclude the wasteful July-surge placements. Hold sale CPA ≤ $55.

### Popup Spec (ALIA)

- Goal: Route intent and capture email/SMS.

- Header: "Buying for someone?"

- Sub: "Get Dad sorted — 15% off mats this week."

- CTA: Gift-buyer → Tradie Dad Pack; self-buyer → mat or Full Rig.

- Style: On-brand, product-led, no tagline.

### Website / Onsite

| Element | Update |
| --- | --- |
| Homepage hero | Father's Day gift message + Pro Mat Plus + offer |
| Sticky banner | Offer + state-aware shipping countdown |
| Landing page | Father's Day gift collection |
| Product page | "Build Your Pack" bundle selector; 15% mat discount auto-applied |
| Popup | Gift/self routing poll (above) |
| Checkout | Gift note option; GWP auto-applied over ~$300 |

## Customer Service & Logistics

What CS needs to know

- Sale runs 26 Aug – 4 Sep; post-FD flash 7–8 Sep (self-buy, 20%).

- 15% off mats; 2-for-$499 includes free shipping; GWP auto-applies over ~$300; the 15% does not stack on the 2-for-$499 pack.

- Shipping cutoffs for Father's Day delivery: QLD, SA, NT, WA, TAS order by Tue 2 Sep; VIC, NSW, ACT by Wed 3 Sep. After a state's cutoff, recommend the digital gift card.

Key FAQs

- When does the sale end? → Friday 4 Sep (two days before Father's Day).

- Will it arrive in time? → If ordered by your state cutoff (2 or 3 Sep). After that, gift card delivers instantly.

- Can I mix colours on the 2-pack? → Yes, any colour combination.

- Is the free gift automatic? → Yes, on orders over ~$300.

- Missed the cutoff? → Digital gift card arrives instantly and covers the offer.

Operational notes

- Confirm stock cover for a 10-day sale across Pro Mat Plus and every bundle component (magnet mat, wipes, keyring/cap, covers, bottle opener).

- Set up bundle SKUs with auto-applied discount and GWP threshold logic.

- Confirm carrier lead times against the advertised cutoffs (assumed calendar days to Father's Day; business-day math may pull cutoffs one day earlier).

- Surface the digital gift card as the last-minute fallback.

## Checklists

Pre-Launch (by 25 Aug)

☐  Board sale date updated to 26 Aug – 4 Sep

☐  Pro Mat COGS confirmed < 42.8% of retail

☐  Bundle SKUs built with discount + GWP logic

☐  Component and GWP prices confirmed; margin model finalised

☐  Stock cover confirmed across all bundle items

☐  Add-to-cart pixel fixed (clean sale tracking)

☐  LPV Flagship / TOF-Broad paused

☐  Gift collection, Build-Your-Pack, banner, popup live

☐  Shipping cutoff dates verified with carrier

Launch (26 Aug)

☐  E1 scheduled and QA'd (links, offer, cutoff, no tagline)

☐  Meta prospecting live on gift angle

☐  Homepage hero + sticky banner countdown live

☐  ALIA gift/self poll live

☐  CS briefed on offer, cutoffs, FAQs

## Success Metrics

- Revenue and GPAM dollars vs the finalised margin model.

- AOV ≥ $315 and bundle attach rate ≥ 30%.

- Gift vs self split (ALIA poll) and post-FD flash conversion.

- Sale CPA ≤ $55; MER ≤ 33%; GPAM protected above break-even.

- New vs returning customer mix; list-driven share of discounted orders.

- Early checkpoint ~30–31 Aug: is the sale pacing to target, or trim spend.

## Internal Guardrail

If it ever feels like:

- A generic percent-off clearance blast,

- Leading with the discount instead of the gift,

- Reaching for the old tagline or novelty gimmicks,

…it's wrong.

It should feel like helping someone give a genuinely useful gift — the mat he'll actually use.

## Open Decisions

- Component prices (magnet mat, wipes, cover, GWP) — to finalise bundle pricing and the ≤20% effective-discount margin check.

- Pro Mat COGS < 42.8% of retail — confirms a discounted mat clears CPA.

- GWP item (Cap / Keyring / Beanie) and threshold (~$300).

- Post-FD flash depth — 20% recommended (list-only, zero CPA) vs matching 15%.

- Board sale date reconciled to 26 Aug – 4 Sep.